## Back-end
BOOKSTORE PART
BACK-END
| Num. | Task | Estimate |  |  | Actual |  |  | Status | Note
|  |  | Effort | Start | End | Effort | Start | End
| 1 | Create User & Role entity | 1h | 18/4 | 18/4 | 1h | 18/4 | 18/4 | Done
| 2 | Security Configuration | 2h | 18/4 | 18/4 | 2h | 18/4 | 18/4 | Done
| 3 | Login & Register & 403 | 4h | 19/4 | 19/4 | 4h | 19/4 | 19/4 | Done
| 4 | UpdateUserInfo | 4h | 19/4 | 23/4 | 4h | 19/4 | 23/4 | Done
| 5 | Create all Entities | 8h | 23/4 | 24/4 | 8h | 23/4 | 24/4 | Done
| 6 | Change source structure | 6h | 24/4 | 24/4 | 5h | 24/4 | 24/4 | Done | 3 part: dataquery, admin, bookstore
| 7 | AddBook & Book List | 2h | 26/4 | 26/4 | 1h | 26/4 | 26/4 | Done
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26

## Front-end
BOOKSTORE PART
FRONT-END
| Num. | Task | Estimate |  |  | Actual |  |  | Status | Note
|  |  | Effort | Start | End | Effort | Start | End
| 1 | Login & Register & 403 Template | 4h | 19/4 | 19/4 | 4h | 19/4 | 19/4 | Done
| 2 | Navbar & Footer Template | 1h | 20/4 | 20/4 | 1h | 20/4 | 20/4 | Done
| 3 | Homepage Template | 5h | 20/4 | 20/4 | 5h | 20/4 | 20/4 | Done
| 4 | UpdateUserInfo Template | 4h | 19/4 | 23/4 | 4h | 19/4 | 23/4 | Done
| 5 | AddBook | 2h | 26/4 | 26/4 | 2h | 26/4 | 26/4 | Done
| 6 | BookList | 1h | 26/4 | 26/4 | 1h | 26/4 | 26/4 | Done
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26