## Back-end
BOOKSTORE PART
BACK-END
Num. | Component | Task | Estimate |  |  | Actual |  |  | Status | Note
|  |  | Effort | Start | End | Effort | Start | End
1 | dataquery | Create User & Role entity | 1h | 18/4 | 18/4 | 1h | 18/4 | 18/4 | Done
2 | admin & bookstore | Security Configuration | 2h | 18/4 | 18/4 | 2h | 18/4 | 18/4 | Done
3 | admin & bookstore | Login & Register & 403 | 4h | 19/4 | 19/4 | 4h | 19/4 | 19/4 | Done
4 | admin & bookstore | UpdateUserInfo | 4h | 19/4 | 23/4 | 4h | 19/4 | 23/4 | Done
5 | dataquery | Create all Entities | 8h | 23/4 | 24/4 | 8h | 23/4 | 24/4 | Done
6 |  | Change source structure | 6h | 24/4 | 24/4 | 5h | 24/4 | 24/4 | Done | 3 part: dataquery, admin, bookstore
7 | admin & dataquery | AddBook & BookList | 2h | 26/4 | 26/4 | 1h | 26/4 | 26/4 | Done
8 | admin & dataquery | CRUD Book | 4h | 27/4 | 27/4 | 5h | 27/4 | 2/5 | Done
9 | bookstore | BookShelf | 4h | 2/5 | 2/5 | 4h | 2/5 | 2/5 | Done
10 | bookstore | BookDetail |  | 3/5 | 3/5
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26

## Front-end
BOOKSTORE PART
FRONT-END
Num. | Component | Task | Estimate |  |  | Actual |  |  | Status | Note
|  |  | Effort | Start | End | Effort | Start | End
1 | admin & bookstore | Login & Register & 403 Template | 4h | 19/4 | 19/4 | 4h | 19/4 | 19/4 | Done
2 | admin & bookstore | Navbar & Footer Template | 1h | 20/4 | 20/4 | 1h | 20/4 | 20/4 | Done
3 | admin & bookstore | Homepage Template | 5h | 20/4 | 20/4 | 5h | 20/4 | 20/4 | Done
4 | admin & bookstore | UpdateUserInfo Template | 4h | 19/4 | 23/4 | 4h | 19/4 | 23/4 | Done
5 | admin | AddBook Template | 2h | 26/4 | 26/4 | 2h | 26/4 | 26/4 | Done
6 | admin | BookList Template | 1h | 26/4 | 26/4 | 1h | 26/4 | 26/4 | Done
7 | admin | BookInfo Template | 1h | 27/4 | 27/4 | 20m | 27/4 | 27/4 | Done
8 | admin | UpdateBook Template | 1h | 27/4 | 27/4 | 20m | 27/4 | 27/4 | Done
9 | bookstore | BookShelf | 2h | 2/5 | 2/5 | 2h | 2/5 | 2/5 | Done
10 | bookstore | BookDetail | 2h | 3/5 | 3/5
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26